## Timeline Overview
NexusAir — 10-Week Development Timeline
Start: February 1, 2025 ¦ End: April 12, 2025 ¦ 4 Weeks Completed (Feb 1 – Mar 1) ¦ Status: Active Development
WK | Phase | Deliverables & Tasks | Status | Feb 1–8 | Feb 8–15 | Feb 15–22 | Feb 22–Mar 1 | Mar 1–8 | Mar 8–15 | Mar 15–22 | Mar 22–29 | Mar 29–Apr 5 | Apr 5–12
1 | Foundation & Setup | Monorepo scaffolding, Electron + Vite setup, FastAPI hello-world sidecar, SQLAlchemy models + Alembic init, CI pipeline (GitHub Actions), README and dev setup docs | ✅ DONE | ███
2 | Core Editor | CodeMirror 6 integration, Markdown rendering, [[wikilink]] and #tag syntax, debounced auto-save to SQLite, document list sidebar, document CRUD API endpoints | ✅ DONE |  | ███
3 | Graph Engine | NetworkX graph service, markdown-it-py AST parser for link extraction, incremental graph update on save, graph visualization panel (react-force-graph-2d), graph stats dashboard | ✅ DONE |  |  | ███
4 | Vector Layer | Sentence Transformers embedding pipeline, LanceDB index setup, async embedding on doc save, cosine ANN search endpoint, basic semantic search UI in sidebar | ✅ DONE |  |  |  | ███
5 | LLM Integration | llama-cpp-python integration, GGUF model download manager UI, model loading/unloading, streaming SSE endpoint /api/ai/stream, basic AI chat panel in renderer | 🔄 IN PROGRESS |  |  |  |  | ███
6 | Retrieval & RRF | Dual-path retrieval (graph BFS + vector ANN), Reciprocal Rank Fusion (RRF) implementation, context_builder.py (dedup + token budget), end-to-end AI query pipeline, retrieval quality eval | ⏳ UPCOMING | [5 empty] | ███
7 | PDF Ingestion & Corpus | PyMuPDF PDF text extraction, block splitting and embedding of PDF content, file import UI (drag-and-drop), metadata tagging from frontmatter, domain lexicon customization | ⏳ UPCOMING | [6 empty] | ███
8 | Polish & UX | Settings panel (model selection, theme, keybindings), keyboard shortcuts, error handling + toast notifications, empty state designs, onboarding wizard for first launch | ⏳ UPCOMING | [7 empty] | ███
9 | Testing & Hardening | pytest integration tests for all API endpoints, vitest unit tests for React components, Playwright E2E test suite, performance profiling (query latency, TTFT benchmarks), bug fixes | ⏳ UPCOMING | [8 empty] | ███
10 | Build & Release | electron-builder packaging (Win/macOS/Linux), SHA-256 model checksum validation, documentation finalization (user guide, API docs), v1.0 release artifacts + changelog | ⏳ UPCOMING | [9 empty] | ███
✅ Completed (Wks 1–4) |  | 🔄 In Progress (Wk 5) |  | ⏳ Upcoming (Wks 6–10)

## Completed — What We Built
NexusAir — Completed Work Log (Weeks 1–4: Feb 1 – Mar 1, 2025)
Everything in this sheet has been built, tested, and merged to main branch.
Week | Phase | Task Completed | What Was Built | Technical Notes | Output/Artifact
1 | Foundation | Monorepo setup | Electron 30 app with Vite renderer, Python FastAPI sidecar scaffolded | electron-builder config, vite.config.js, package.json workspaces | / project root running
1 | Foundation | CI pipeline | GitHub Actions: lint + pytest + vitest on every push to main | test.yml: black check, eslint, pytest --cov, vitest run | .github/workflows/test.yml
1 | Foundation | DB schema | SQLAlchemy async models: Document, Block, Link, Tag tables with Alembic migration v001 | aiosqlite engine, async session factory, alembic.ini configured | backend/db/migrations/001_init.py
2 | Editor | CodeMirror 6 editor | Full markdown editor with syntax highlighting, block-level editing, line wrapping | @codemirror/view + @codemirror/lang-markdown extensions wired to React | src/renderer/components/Editor/BlockEditor.jsx
2 | Editor | Wikilink syntax | Custom CodeMirror extension: [[wikilinks]] highlighted and clickable, #tags detected | mdit-py-plugins wikilink plugin on Python side; Lezer grammar extension on JS side | src/renderer/components/Editor/extensions/
2 | Editor | Document CRUD API | GET /documents, POST /documents, PUT /documents/{id}, DELETE /documents/{id} | Pydantic request/response models, async SQLAlchemy CRUD helpers, 200/404/422 responses | backend/routers/documents.py
3 | Graph Engine | NetworkX graph service | GraphService class: build_from_db(), update_node(), get_graph_json() for renderer | Directed DiGraph, weighted edges by link frequency, cycle detection guard | backend/services/graph_service.py
3 | Graph Engine | AST link parser | markdown-it-py parses [[wikilinks]] and #tags from document content on every save | Token stream parsed, link targets resolved against documents table by title slug | backend/services/graph_service.py:parse_links()
3 | Graph Engine | Graph viz panel | react-force-graph-2d canvas panel: click-to-navigate, zoom, edge opacity by weight | Graph JSON fetched from GET /api/graph/nodes, D3-force layout, node color by tag | src/renderer/components/Graph/GraphPanel.jsx
4 | Vector Layer | Embedding pipeline | Sentence Transformers all-MiniLM-L6-v2 generates 384-dim embeddings per block on save | Async background task (asyncio.create_task) to avoid blocking API response | backend/services/vector_service.py:embed_and_upsert()
4 | Vector Layer | LanceDB index | LanceDB nexusair_blocks table with IVF-PQ index, cosine similarity, upsert on change | pyarrow schema, lancedb.connect(data/vectors/), index created after 256 rows | backend/services/vector_service.py
4 | Vector Layer | Semantic search UI | Search bar in sidebar: real-time ANN search results with snippet preview and score | Debounced POST /api/search with {query, top_k}, results rendered in SidebarSearch component | src/renderer/components/Sidebar/SidebarSearch.jsx

## Upcoming — Weeks 5–10
NexusAir — Upcoming Weeks Plan (Weeks 5–10: Mar 1 – Apr 12, 2025)
Weeks 5–10: LLM integration → retrieval → PDF ingest → polish → testing → release
Week | Phase | Key Tasks | Definition of Done | Dependencies | Priority
5 | LLM Integration | llama-cpp-python sidecar, model download manager, SSE /api/ai/stream endpoint, AI chat panel with streaming renderer | User can load Llama 3 locally, type a query, and see streaming tokens appear in chat UI | Weeks 1–4 complete, GGUF models available on HuggingFace Hub | 🔴 Critical
6 | Retrieval & RRF | graph BFS (N-hop), LanceDB ANN parallel fetch, RRF fusion algorithm, context_builder.py, dedup + token budget, E2E query eval | AI query uses both graph + vector retrieval; RRF-merged context fed to LLM; grounding accuracy > 80% | Week 5: InferenceService working, Week 4: VectorService stable | 🔴 Critical
7 | PDF Ingestion | PyMuPDF PDF text/image extraction, block splitter, drag-and-drop import UI, frontmatter parser for markdown imports, metadata tagging | User can drag PDF into app; content is chunked, embedded, and queryable within 30 seconds | Week 4: VectorService, Week 6: context pipeline stable | 🟠 High
8 | Polish & UX | Settings panel (model select, theme), keyboard shortcuts map, error toast system, empty states, onboarding wizard for first-time users | New user can open app, complete onboarding, and make first AI query within 3 minutes | Weeks 5–7 features stable enough to wrap with UX | 🟠 High
9 | Testing & Hardening | pytest API integration tests, vitest component tests, Playwright E2E suite, query latency profiling (P95 < 200ms), TTFT benchmark, bug fixes from testing | All tests pass; P95 query latency < 200ms; TTFT < 3s on 8GB RAM hardware; zero critical bugs | All features complete (Weeks 5–8) | 🔴 Critical
10 | Build & Release | electron-builder (Win/macOS/Linux), GGUF checksum validation, user guide doc, API reference, v1.0 CHANGELOG, GitHub release artifacts | Downloadable installers for all 3 platforms; docs published; v1.0 tag pushed to GitHub | Week 9: all tests passing | 🔴 Critical